# VFIHA Indigenous Jersey Crest

# Design Selection Process

Stage 1:  Call for Proposal

- Refer to latest version of:  “Vancouver Female Ice Hockey Association - Call for Proposal to Musqueam, Squamish and Tsleil-Waututh Nations; Artists - Jersey Crest”

- Distribution Date:  Tuesday, May 10, 2022

- Create Evaluation Panel in preparation for Stage 2 (by Saturday, June 11, 2022)

  - At least 6 to 8 people with different perspectives:

      - VFIHA President

      - VFIHA Communications Manager

      - At least 2 Indigenous people (VFIHA members/parents and non-members)

      - Someone with graphic arts experience/branding person

      - Young player

      - Older player

      - Coach

      - Official

    - Final Date for Receipt of Applications:  Saturday, June 11, 2022

Stage 2:  Review of Applications

- As the applications are received, format them into a standard style and distribute to the Evaluation Panel.

- Up to 2x 1 hour sessions to short list to 6 artists

- Complete by Saturday, June 18, 2022

Stage 3:  Develop Concept Design

- Have a workshop with 6 finalists and Evaluation Panel:

  - This is a co-design process

  - Artist’s agreement would be signed at this time

  - Re-emphasize time frame to artists with the understanding that not meeting our schedule will be end of engagement.

  - Describe what we want:

    - An animal or creature (of the land, water, sky and/or spirit).

    - To be connected to the culture and stories of the artist’s nation.

    - An explanation of the crest’s connection to the land we live on and the cultural significance for the local First Nation.

  - Final drafts by Saturday, July 16, 2022

  - All 6 artists to be paid $250 each for the above.  No payment if not submitted by Saturday, July 16, 2022.

Stage 4:  Selection Process

- Members (i.e. players & goalies) choose their preferred top 3 of 6 submitted concept designs through preferential voting

- Final decision weighted:

  - 50% from preferential voting result

  - 50% from Board

State 5:  Final Design Process

- Artist finalises design by an agreed date with the VFIHA Board and provides artist’s statement on the design, e.g. initial sketches, reasoning behind the design, cultural context.

- Finalist to retain copyright ownership and to be paid for VFIHA perpetual exclusive all rights use.

- Payment on receipt of design in the required file formats and the artist’s written statement of the design.